## EXAMPLE – Agile Epic Req
Agile Epic Requirements Template – Example
1. Epic Overview
EPIC NAME
Real-Time EV Charging Station Monitoring
EPIC OWNER |  | EPIC ID | CREATION DATE | LAST UPDATED
Alexandra |  | PC-EPIC-001 | 07/22/20XX | 07/22/20XX
2. Epic Description
SUMMARY
Implement a real-time monitoring system for EV-charging stations to provide instant status updates and alerts.
DETAILS
This epic involves developing a robust monitoring solution that integrates with all charging stations, enabling real-time data collection and analysis. The system will display station availability, charging status, and performance metrics on a centralized dashboard.
GOALS (STORIES) – Functional Requirements
– Enhance operational efficiency by providing up-to-date station status. – Improve user satisfaction with real-time availability updates. – Enable proactive maintenance by identifying potential issues early.
3. Business Case (Non-Functional Requirements)
VALUE PROPOSITION
The real-time monitoring system will increase the efficiency and reliability of our EV-charging network, leading to higher customer satisfaction and reduced downtime.
SUCCESS CRITERIA
– Achieve 95% accuracy in real-time status updates. – Reduce downtime by 20%. – Receive positive feedback from at least 80% of users in post-implementation surveys.
4. Acceptance Criteria
CONDITIONS OF SATISFACTION
– The dashboard must display real-time status updates with less than a five-second delay. – The system must send alerts for any significant status changes or issues.
DEFINITION OF DONE (DoD)
– Code is reviewed and approved. – All unit and integration tests are passed. – User documentation is updated. – Stakeholder approval is obtained.
6. User Stories and Tasks
User Story ID | Story Name
PC-US-001 | Receive Status Alerts
User Story Description
As a maintenance team member, I want to receive alerts when a station goes offline so that I can address issues promptly.
Acceptance Criteria
The system must send alerts within one minute of a status change.
TASKS
Task ID | Task Name |  | Description
PC1-TASK-001 | Develop Real-Time API Integration |  | Create an API to collect real-time data from charging stations.
PC1-TASK-002 | Build Monitoring Dashboard |  | Develop a user interface to display real-time data.
PC1-TASK-003 | Implement Alert System |  | Create a system to send alerts based on predefined conditions.
PC1-TASK-004 | Conduct User Testing |  | Perform testing with a select group of users to gather feedback and identify issues.
User Story ID | Story Name
PC-US-002 | View Charging Station Status
User Story Description
As a engineer , I want to view charging station status so that I get all information about the charging station, and notice any problem immediately.
Acceptance Criteria
The dashboard must show the real-time status of each station.
TASKS
Task ID | Task Name |  | Description
PC2-TASK-001 | Get real time information |  | Create an API to collect real-time data from charging stations.
PC2-TASK-002 | Check error or problem |  | Implement anomaly detection logic to identify potential issues with charging stations
PC2-TASK-003 | User interface |  | Implement real-time updates to ensure that status information can be dynamically refreshed.
User Story ID | Story Name
PC-US-003 | identifying potential issues early.
User Story Description
As a Safety officer , I want to identifying potential issues early so that I can make the losses are minimized.
Acceptance Criteria
The issus should alert immediately.
TASKS
Task ID | Task Name |  | Description
PC3-TASK-001 | Check real time data |  | The issus should inform the office at the first time
PC3-TASK-002 | Make an alert system |  | The condition should be checked if it is the emergency
PC3-TASK-003 | Find similar issue |  | System can search the database to find the issue have happened before and fix it, if not, record the issue.
6. Timeline | Thursday, August 1, 20XX |  | Monday, September 30, 20XX
MILESTONE |  |  | DATE OF MILESTONE
API Integration Complete |  |  | Thursday, August 15, 20XX
Dashboard Development Complete |  |  | Monday, September 2, 20XX
User Testing Complete |  |  | Friday, September 20, 20XX
Final Review and Sign-Off |  |  | Monday, September 30, 20XX
7. Stakeholders
– Project Manager: Everett – Product Owner: Brooklyn – Development Team Lead: Henry – UAT Lead: Romy
8. Risks and Assumptions
RISKS | MITIGATION PLANS |  | ASSUMPTIONS
Potential delays in data integration from charging stations may occur. | Hold regular status meetings to monitor progress and address issues promptly. |  | All charging stations are capable of providing real-time data.
Unforeseen technical challenges in real-time data processing may arise. | Allocate additional resources for data integration tasks. |  | Required APIs are available and functional.
9. Resources
TEAM MEMBERS
NAME |  | TITLE
Henry |  | Development Team Lead
Jason |  | Backend Developer
Makara |  | Frontend Developer
Sasha |  | QA Engineer
TOOLS AND TECHNOLOGY
– API Gateway – Real-Time Data Processing Framework – Web Dashboard Framework
10. Progress Tracking |  |  | STATUS
In Progress
PROGRESS UPDATES
API integration development started on August 1, 20XX.
Initial dashboard design completed on August 10, 20XX.
11. Comments and Notes
Any additional notes or comments related to the epic can be added here for reference.

## BLANK – Agile Epic Req
Agile Epic Requirements Template
1. Epic Overview
EPIC NAME
Mobile APP for Online Retailer
EPIC OWNER |  | EPIC ID | CREATION DATE | LAST UPDATED
Alexandra |  | MOB-EPIC-001 | 07/22/20XX | 07/22/20XX
2. Epic Description
SUMMARY
Develop a mobile app for an online laptop retailer to enhance customer experience and engagement.
DETAILS
The app will include features such as augmented reality (AR) for virtual laptop configuration, a chatbot for customer queries, and loyalty rewards (discounts and promo codes). The app will be tested and launched after all user stories are completed.
GOALS
– Provide an immersive shopping experience with AR features. – Improve customer support through a chatbot. – Reward loyal customers with discounts and promo codes.
3. Business Case
VALUE PROPOSITION
The mobile app will increase customer engagement, improve satisfaction, and drive sales for the online laptop retailer.
SUCCESS CRITERIA
– Achieve a 90% user satisfaction rate in post-launch surveys. – Increase customer retention by 15% within six months. – Reduce customer support queries by 20% through the chatbot functionality.
DEPENDENCIES
– Availability of AR development tools. – Integration with existing loyalty and discount systems. – Access to customer data for chatbot functionality.
4. Acceptance Criteria
CONDITIONS OF SATISFACTION
– AR features must allow customers to visualize laptops in real-time. – Chatbot must resolve 80% of customer queries without escalation. – Loyalty rewards must be applied automatically at checkout.
DEFINITION OF DONE (DoD)
– All features are tested and approved. – Code is reviewed and meets quality standards. – User documentation is complete and stakeholders have signed off.
5. User Stories and Tasks
USER STORIES
User Story ID | Story Name
MOS-US-001 | AR Virtual Laptop Configuration
User Story Description
As a customer, I want to use AR to visualize different laptop configurations so I can make an informed decision.
Acceptance Criteria
AR must load laptop models in real-time and allow customization with less than 5 seconds delay.
TASKS
Task ID | Task Name |  | Description
MOB1-TASK-001 | Develop AR Integration |  | Create AR functionality for visualizing laptop configurations.
MOB1-TASK-002 | Test AR Features |  | Test AR functionality across different devices and network conditions.
USER STORIES
User Story ID | Story Name
MOB-US-002 | Chatbot for Customer Support
User Story Description
As a customer, I want to use a chatbot to resolve small queries so I can get instant support.
Acceptance Criteria
Chatbot must resolve 80% of queries without escalation.
TASKS
Task ID | Task Name |  | Description
MOB2-TASK-001 | Build Chatbot Framework |  | Develop a chatbot framework for handling customer queries.
MOB2-TASK-002 | Train Chatbot Model |  | Train the chatbot model with FAQs and common queries.
RISKS | MITIGATION PLANS |  | ASSUMPTIONS
AR features may not work seamlessly on all devices. | Test AR functionality on a wide range of devices during development. |  | Customers have devices capable of running AR features.
Chatbot may not handle complex queries effectively. | Regularly update the chatbot model with new queries and responses. |  | Customers will use the chatbot for simple queries only.
Loyalty system integration may encounter technical issues. | Conduct thorough testing of the integration before launch. |  | The loyalty system is stable and provides required APIs.
9. Resources
TEAM MEMBERS
NAME |  | TITLE
Jerry |  | Development Team Lead
Harry |  | Backend Developer
Ron
Hermione |  | Frontend Developer
TOOLS AND TECHNOLOGY
AR Development Tools Chatbot Framework Loyalty System API
10. Progress Tracking |  |  | STATUS
PROGRESS UPDATES
AR feature development started on [Insert Date].
Chatbot framework completed on [Insert Date].
11. Comments and Notes
Any additional notes or comments related to the epic can be added here for reference.